# Grant Review Preparatory Checklist

## Palau FY27 Title V Block Grant Review & FSM FY27 Title V Block Grant Review

Status: In Progress | Updated: July 30, 2026 | Project End Date: September 15, 2027

## REVIEWER ROLE

Glenn is one of THREE reviewers for each jurisdiction:

• Palau FY27 review (September 14, 2027) - 3-reviewer team

• FSM FY27 review (September 15, 2027) - 3-reviewer team

## PHASE 1: WORKSPACE & REFERENCE MATERIALS

Notion Organization

[ ] Create FY27 - CURRENT CYCLE organizational cluster

[ ] Create FY27 Reviewer Resources sub-page

[ ] Upload/link MCHB FY27 Guidance by Domain

[ ] Upload/link MCHB Glossary of Key Terms

[ ] Add reference note with review timeline (9/10 deadline, 9/14 & 9/15 meetings)

Document Accessibility

[ ] Confirm all materials accessible in Notion

[ ] Create quick reference for 2 Universal NPMs

[ ] Store printed copies locally if preferred

## PHASE 2: PALAU & FSM MATERIALS INVENTORY & VERIFICATION

[ ] Verify all Palau database rows are populated and accessible

[ ] Verify all Palau PDFs load without errors

[ ] Access FY26 Palau materials for comparison

[ ] Access FSM FY27 materials

## PHASE 3: GUIDANCE ANALYSIS & COMPARISON

[ ] Read MCHB_FY27_Guidance_by_Domain

[ ] Read MCHB_Glossary_Key_Terms

[ ] Identify NPMs selected by Palau

[ ] Identify NPMs selected by FSM

[ ] Finalize FY26 vs. FY27 comparison for both jurisdictions

## PHASE 4: REVIEWER ROLE CLARIFICATION

Two Review Lenses (Glenn's Specialty)

[ ] Family-Centered Care Lens: Prepare analysis framework

[ ] Pacific Islander Cultural Lens: Prepare analysis framework

Coordination with Co-Reviewers

[ ] Identify co-reviewers for Palau (2 additional reviewers)

[ ] Identify co-reviewers for FSM (2 additional reviewers)

[ ] Establish communication plan for reviewer coordination

[ ] Clarify review expectations and format for written comments

## PHASE 5-9: DATA GATHERING, ANALYSIS, FRAMEWORKS & FINAL PREPARATION

[ ] Gather Palau epidemiologic data (mortality rates, access measures)

[ ] Gather FSM epidemiologic data

[ ] Review prior year feedback for both jurisdictions

[ ] Set up Notion tracking for findings by domain (both jurisdictions)

[ ] Decide on annotation method (Notion vs. offline)

[ ] Develop Family-Centered Care review framework

[ ] Develop Pacific Islander Cultural Lens framework

[ ] Deep dive into Palau application review

[ ] Deep dive into FSM application review

[ ] Apply both review lenses to each jurisdiction

[ ] Compile findings and identify key points for written comments

## PHASE 10: CRITICAL TIMELINE & MILESTONES

Preparation Phase (July 2026 – August 2027)

[ ] Complete all foundational work (workspace, materials, guidance, data gathering)

[ ] Develop specialized review frameworks (family-centered, cultural)

[ ] Deep dive analysis of Palau and FSM applications

Final Writing Period (September 1–9, 2027)

[ ] Finalize all review analysis and findings for Palau

[ ] Finalize all review analysis and findings for FSM

[ ] Complete written reviewer comments for Palau

[ ] Complete written reviewer comments for FSM

[ ] Coordinate with co-reviewers if sharing draft findings

### CRITICAL: Written Comments Submission (September 10, 2027)

BY SEPTEMBER 10, 11:59 PM:

[ ] PALAU: Submit final written reviewer comments

[ ] FSM: Submit final written reviewer comments

[ ] Confirm submission received by MCHB/regional office

In-Person Review Meetings

Palau Review Meeting – MONDAY, SEPTEMBER 14, 2027

[ ] Glenn attends as one of three reviewers

[ ] Review written feedback with Palau team

[ ] Collaborate with two co-reviewers

[ ] Engage on priorities and strategies

FSM Review Meeting – TUESDAY, SEPTEMBER 15, 2027

[ ] Glenn attends as one of three reviewers

[ ] Review written feedback with FSM team

[ ] Collaborate with two co-reviewers

[ ] Engage on priorities and strategies

Project Complete – All work with both jurisdictions concluded

## COMPLETION TRACKING

| Phase | Status |
| --- | --- |
| Phase 1: Workspace | In Progress |
| Phase 2: Materials Inventory | Ready |
| Phase 3: Guidance Analysis | Ready |
| Phase 4: Reviewer Role | One of 3 reviewers |
| Phase 5-9: Prep & Analysis | In Progress |
| Phase 10: Timeline | Ends 9/15/2027 |

Document Version: Review Prep Checklist v3 (Final Timeline)

Updated: July 30, 2026

CRITICAL DATES: 9/10 Written Comments | 9/14 Palau Meeting | 9/15 FSM Meeting | PROJECT ENDS